## Writing Launch Plan
WRITING LAUNCH PLAN
PHASE |  | DETAILS |  | Q2 |  |  |  | Q3 | [12 empty] | Q4 |  |  | Q1
|  |  |  | JUN |  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT | NOV | DEC | JAN | FEB | MAR
|  |  | NOTES | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25
1 | Get Educated & Inspired | Work through all newsletters in Writing Folder | bar: JUN 5
|  | Weekly Reading: Substack, Writing Newsletters | [18 empty] | ongoing | bar: JUN 5 to SEP 25
|  | Weekly LinkedIn Activity | [18 empty] | ongoing | bar: JUN 5 to JUN 26; SEP 4 to SEP 25
Sign up for 2 Leadership Substack Writers | bar: JUL 3
Research other ways to monetize
2 | Strategize & Plan | Finish Author Brand Identity Guide | bar: JUN 5
Develop Elevator Speech | bar: JUN 12
Review / Organize "Notes" App writing folder/content
|  | Platform Build Research & Planning | [18 empty] | X | bar: SEP 4 to SEP 25
|  | Clarify Brand Identity & Ideal Client (Rachel) | Give Rachel Substack Strategy Doc; Ideal Audience sheet from Mercury | bar: SEP 4 to SEP 25
Business Map & Ecosystem Analysis (Rachel) | bar: SEP 4 to SEP 25
|  | Key Messaging & Substack Naming (Rachel) | ADD for Rachel: LinkedIn as part of strategy | bar: SEP 4 to SEP 25
Identify Visual Branding Needs (Rachel) | bar: SEP 4 to SEP 25
Phase 2 Deliverables (map out when we know more) (Rachel)
3 | Create Platform Foundation | Update Website
Update LinkedIn Profile
4 | Launch My Offerings: SUBSTACK more detail on "Substack Launch Plan" | Create Substack Strategy Doc | bar: JUN 5 to JUN 26
Read former Substack newsletters
|  | Weekly Review Substack Launch Plan - add to ToDoIst, update GAANT | [20 empty] | ongoing | bar: AUG 28 to SEP 25
Plan how to integrate my website/blog into writing strategy, then standardize
Build out mechanics of Substack platform (layout, branding)
Create plan for first 3 months of content
Write initial content
Update Contact List for 2023 | bar: JUN 5 to JUN 26; SEP 18
Recruit early adopters to sign up before public launch
Teasers for Launch on LinkedIn, etc.
LAUNCH: Invite Contacts; Post on LinkedIn
Implement Substack Routines
| Launch My Offerings: PUBLISHED ARTICLES & WHITEPAPERS | Research other Publications
Watch Ericka's 2 classes
Set up call with Ericka?
Write "Redefining" Whitepaper
Start trying to get published in journals, magazines, websites
Book Mapping Course | bar: JUN 5 to JUN 26
| Launch My Offerings: BOOK | Build a book club / early adopters
Purchase/orient to Scrivener | bar: JUN 12 to JUN 19; JUL 3
Get early endorsements
Query agents + land an agent
Write proposal | bar: JUL 3 to JUL 24
Refine proposal | bar: SEP 4
Ariel finalize proposal by Sep 29 | bar: SEP 25
Complete proposal
|  | Shop Proposal with Publishers | [19 empty] | as soon as I have an Agent
GET A BOOK DEAL
| Launch My Offerings: OTHER | Pitch myself to podcasts
Update Website
Update Linked
Offer virtual events & courses
Book speaking gigs
Post regularly (every day-ish) on LinkedIn
5 | Systems/Structures | Schedule regular weekly writing/tending time + Retreats | bar: JUL 3
What to Delegate to Jill from this list? | bar: JUL 3
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Including emails from Substack (how to use the platform)
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Like/Comment/Re-Post
Note on G11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: o Could do a Lifetime price for founding members o Affiliate links o Sponsorshio o Partnerships o Ads
Note on G13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See doc started in 2022 Reply: As well as 2023 ppt
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What I am up to and why Reply: Ryan Holiday’s formula
Note on G18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deliverable: visual business map
Note on G19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deliverables: Revised IG bio and intro statement / elevator pitch / substack name & branding
Note on G21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: launch plan, content planner, graphic templates, substack graphic elements, website revision
Note on G24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Newsletter signup front and center on every page
Note on G25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fill it out to the 100% mark Reply: o Link your profile to your blog and Twitter posts so that these automatically post on LinkedI Reply: o Request and give recommendations
Note on G32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ex: put a few key Substack articles I’ve written on my website and link to them Reply: question to explore – should I repost as a LinkedIn article, or just share on my feed linking back to my website?
Note on G41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See Publications & Platforms tab Reply: Pitch & Publish has great info on this in her emails, like this one – at the bottom)
Note on G45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Write for other people’s blogs
Note on G47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Combine with Substack focus group
Note on G49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Get early endorsements. In your proposal, you'll want to include a list of potential endorsers, but if you can go a step further and actually get just a few early statements of support, all the better!
Note on G57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ariel says do this ASAP before you pitch your proposal. Be EVERYWHERE online
Note on G60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do online events about my book topic - proof of concept - ex: Leadership Revolution
Note on G61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The Successful Speaker book
Note on G63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Get Jill’s help again with finances and time Writing Retreats (tending = active on LinkedIn, research/reading/planning; regular reading of other Substacks & Substack guides)